# Laramie County Master Gardeners

## Geodesic Dome Greenhouse Project – Task Timeline: March 2026 – January 2028

Based on grant agreements, applications, and contract requirements. All reimbursement deadlines and reporting obligations are derived from Contract AG252899 (Wyoming Department of Agriculture Subrecipient Grant Agreement).

| Date | Task / Action Item | Source Document | Notes |
| --- | --- | --- | --- |
| MARCH 2026 |  |  |  |
| March 2026 | Confirm greenhouse dome contractor selection and notify via written agreement (Kommi and Dillon) | WY Dept of Agriculture Grant | Contractor to assemble supplies and manufacture struts/connectors for geodome kits by April 2026 |
| March 2026 | Purchase items from dome grant budget list) (Kommi & Tammy) Establish | WY Dept of Agriculture Grant |  |
| March 2026 | Registration for WyoGives 2026 opens March 16, 2026 through WyoGives.org. |  | LCMG can participate in WyoGives on July 15, 2026 |
| March 2026 | Meeting of LCMG social media leaders to plan WyoGives launch |  |  |
| March 2026 | Partner with large and small donors for for WyoGives matches |  |  |
| March 2026 | Ensure Certificate of Good Standing is current with WY Secretary of State | WY Dept of Agriculture Grant | Required prior to project work |
| APRIL 2026 |  |  |  |
| April 2026 | Begin site preparation – groundbreaking and deep excavation for primary climate battery manifold and Dome #1 (Kommi & Dillon) | FCSAmerica Grant Application | Mini-excavator rental; first dome construction begins |
| April 1, 2026 | Procure all approved supplies (fence pickets, poly cover, aluminum shutters, lumber, fasteners, irrigation materials, etc.) (Kommi & Tammy) | WY Dept of Agriculture Grant – Supplies List | 48 supply line items totaling $24,393/5=$4878.6 plus extra for buying polycarbonate cover rather than polyethylene cover |
| April 1, 2026 | Submit first reimbursement payment voucher to WY Dept of Agriculture (reimbursements begin Jan 15, 2026 then quarterly) (Kommi & Tammy) | WY Dept of Agriculture Grant | Quarterly reimbursement cycle |
| April 15, 2026 | Upon receipt of FCSA funds: Procure all approved supplies (see materials list for climate batteries) (Kommi & Tammy) | FCSAmerica Grant budget Application |  |
| April–May 2026 | Install climate battery layers (2ft and 4ft and 6ft) for Dome #1; begin structural assembly of Dome #1 | FCSAmerica Grant Application/ WY Dept of Agriculture Grant | Sensor array deployment included |
| April–June 2026 | Laramie County Conservation District will install a windbreak and an irrigation system along the west and north side of Lot #1 and on the north side of Lot #2 the site |  |  |
| April–June 2026 | Wyoming State Forestry will install fruit trees and berry shrubs on Lot #2 |  |  |
| Apr–Aug 2026 | Groundbreaking; excavation & climate battery installation (Domes #1–#3); dome materials procurement (WY Dept of Ag grant); Lowe’s fence & rainwater materials ordered; electrical trenching begins | FCSAmerica Grant; WY Dept of Agriculture Grant; Lowe’s Hometowns Grant; WyCF Grant | Mini-excavator rental; fence procurement and staged delivery; Black Hills Energy trenching coordination |
| MAY 2026 |  |  |  |
| May 2026 | Complete Dome #1 construction and begin initial crop cycles | FCSAmerica Grant Application |  |
| May–Jun 2026 | Dome #1 operational; first crop cycles & educational workshops begin; Lowe’s fence installation; rainwater harvesting network activation; perimeter lighting installation; WyCF grant award notification expected | FCSAmerica Grant; WY Dept of Agriculture Grant; Lowe’s Hometowns Grant; WyCF Grant | Dome #1 first full growing cycle; fence and rainwater system activated; watch for WyCF award letter |
| JUNE – OCTOBER 2026 |  |  |  |
| Jun–Oct 2026 | Sequential rollout Domes #2–#3 with climate batteries; aquaponics system installation (WCLC grant); orchard drip irrigation operational; community programming season at full capacity | FCSAmerica Grant; WY Dept of Agriculture Grant; WCLC Grant; WyCF Grant | One dome at a time through October; aquaponics fish stocking and plant seeding; drip irrigation serving all orchard trees and shrubs |
| June 2026 | Begin sequential construction of Domes #2 through #5 – install climate batteries and structures for each | FCSAmerica Grant Application | One dome at a time through October |
| June 1, 2026 | Submit quarterly reimbursement voucher to WY Dept of Agriculture | WY Dept of Agriculture Grant | Include documentation of expenditures |
| June 2026 | Launch first educational workshops in Dome #1 (horticulture, sustainability, specialty crops) | WY Dept of Agriculture Grant – Project Purpose | Workshops for schools, 4-H, and community |
| June 2026 | Continue educational workshops and school partnership programming across active domes | WY Dept of Agriculture Grant | Boys & Girls Club, local schools, 4-H, FFA |
| July 2026 | Complete Domes #2 and all individual climate battery installations | FCSAmerica Grant Application/ WY Dept of Agriculture Grant | Target completion before November integration |
| September 1, 2026 | Submit quarterly reimbursement voucher to WY Dept of Agriculture | WY Dept of Agriculture Grant | Q3 reimbursement cycle |
| Nov 2026 | Master Hub integration in operational shed; full-cluster automation testing; system winterization; final grant reporting for WY Dept of Ag (Oct 31 annual report deadline) | FCSAmerica Grant; WY Dept of Agriculture Grant | GrowDirector Controller Hub & Multi-Zone Sensor Array; Oct 31 PPR deadline — ensure submitted on time |
| NOVEMBER 2026 |  |  |  |
| November 2026 | Integrate centralized Master Hub in the operational shed; begin full-cluster software and hardware automation testing | FCSAmerica Grant Application | GrowDirector Controller Hub & Multi-Zone Sensor Array |
| November 2026 | Submit quarterly reimbursement voucher to WY Dept of Agriculture | WY Dept of Agriculture Grant | Q4 reimbursement cycle |
| DECEMBER 2026 |  |  |  |
| December 2026 | Project completion – full system commissioning of all 5 geodesic dome greenhouses and climate battery cluster | FCSAmerica Grant Application | Reverse-return manifold system fully operational |
| OCTOBER 31, 2026 – DEADLINE |  |  |  |
| Oct 31, 2026 | Submit 1st Annual Performance Progress Report (PPR) to WY Dept of Agriculture | WY Dept of Agriculture Grant | Electronic format per Attachment C; must include progress on all objectives from Attachment A |
| 2027 |  |  |  |
| Feb 2027 | Submit quarterly reimbursement voucher | WY Dept of Agriculture Grant | Q1 2027 |
| Spring 2027 | Continue crop production cycles; begin second growing season across all 5 domes | WY Dept of Agriculture Grant – Long-Term Goals | Target 9–10 month growing season |
| Spring–Fall 2027 | Continue educational programming – workshops, school field trips, 4-H and FFA programs, Boys & Girls Club sessions | WY Dept of Agriculture Grant | Collect participant survey data (Indicator 2.1 – stakeholders gaining technical knowledge) |
| May-July 2027 | Complete Domes #3-#5 | WY Dept of Agriculture Grant | Target completion before November integration |
| May 2027 | Submit quarterly reimbursement voucher | WY Dept of Agriculture Grant | Q2 2027 |
| Summer 2027 | Measure and document produce donations to food pantries (e.g., St. Joseph's Food Pantry) | FCSAmerica / WY DoA Grant | Baseline was 470+ lbs in 2024; track progress toward increased output |
| Aug 2027 | Submit quarterly reimbursement voucher | WY Dept of Agriculture Grant | Q3 2027 |
| Fall 2027 | Expand demonstration garden with native plants, shrubs, and trees; document biodiversity outcomes | FCSAmerica Grant Application | Living classroom component |
| Nov 2027 | Submit quarterly reimbursement voucher | WY Dept of Agriculture Grant | Q4 2027 |
| Oct 31, 2027 | Submit 2nd Annual Performance Progress Report (PPR) to WY Dept of Agriculture | WY Dept of Agriculture Grant | Electronic format per Attachment C; cumulative progress on all objectives |
| JANUARY – SEPTEMBER 2028 |  |  |  |
| Jan 2028 | Submit quarterly reimbursement voucher | WY Dept of Agriculture Grant | Q1 2028 |
| By Sept 1, 2028 | Ensure all grant funds are expended or encumbered; report any remaining unspent funds to WY Dept of Agriculture | WY Dept of Agriculture Grant | Unspent funds will no longer be eligible for reimbursement after this date |
| Sept 29, 2028 | Submit Final Report to WY Dept of Agriculture (written + electronic) | WY Dept of Agriculture Grant | Must include: cumulative expense accounting, future promotion/expansion plans, proof of 25% match requirement |
| Sept 29, 2028 | Submit final reimbursement payment request to WY Dept of Agriculture | WY Dept of Agriculture Grant | Final deadline – expenses must be within grant period of performance |

Key Contacts: Kormakur Hognason (VP, LCMG) – vp@lcmg.org – 307-761-1584  |  Agency Contact: Michelle MacDonald – michelle.macdonald@wyo.gov – 307-777-7323